## Overview
Test Plan Identifier | TP-TASKS-LOGIN-UI-001
Product | Calmplete Task Manager (Web)
Version | 1
Created By | Vladimir
Created Date | 2025-11-20
Environment | Web(Firefox, Chrome, Edge)
URL | Client: https://calmplete.net, API: https://api.calmplete.net/swagger
Feature under Test | Email & Password Login (Web UI)

## Introduction
Purpose of the App: | This app allows users to manage daily tasks: create tasks, schedule them, update statuses, and mark them as completed. Authentication is required to access task management features.
Purpose of testing: | To verify that the Email & Password login functionality works as expected and allows users to securely access task management features including validation behaviour, error messages, and redirect to the Tasks Dashboard after successful login.
Environmental needs: | Testing must be executed on the deployed environment at: http://calmplete.net (client) and http://api.calmplete.net/swagger (server). UI elements, workflows, and error handling must be validated before release.
Risk Factors | Over-strict client-side validation can block valid users (e.g. whitespace in email).
Strategy / Approach | Functional testing of login flows (positive/negative).

## EntryExit Criteria
Entry Criteria:
1 | Requirements for Email & Password Login (Web UI) are completed and reviewed.
2 | Test environment (client & API) shall be deployed and accessible at: http://calmplete.net and http://api.calmplete.net/swagger
3 | Test data (valid test user accounts) shall be prepared.
4 | All necessary UI elements shall be available and stable for testing.
5 | At least one user with confirmed email exists for positive scenarios
6 | Non-existing / wrong-password combinations identified for negative scenarios.
Exit Criteria:
1 | 100% of functional test cases for Email & Password Login (Web UI) are executed.
2 | All Critical and Major defects shall be fixed and verified.
3 | All planned functional test cases shall be executed.
4 | All Critical/Major defects for Email & Password Login are either fixed and retested, or explicitly accepted by stakeholders.

## Roles
Name | Role | Functionality | Test Scenarios
Vladimir | Manual QA | Login via Email/Password | TC-CL-001 — TC-CL-010

## In-ScopeOut-of-Scope
In-Scope | Functional / UI testing only.
| Page | Access | Functionality | Test Scenarios (TC-MU)
| Login Page | Public | Email & Password Authentication | Test Scenarios (TC-CL)
Out-Scope | Backend Testing, API testing, Performance Testing, Security Testing.
| Page | Access | Functionality
Google Login
Facebook Login
Registration
Password Reset
Tasks

## Test Cases
Metric | Value
Total Test Cases | 10
Executed | 10
Passed | 8
Failed | 2
Blocked / Not Run | 0
TC-CL-001
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify that user is able to log in using a valid email and valid password.
Pre-requisites: | User account with confirmed email exists in the system.
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter valid email | Email field accepts input
3 | Enter valid password | Password field accepts input
4 | Click “Login” button | User is redirected to Tasks Dashboard
TC-CL-002
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify that login fails when incorrect password is entered.
Pre-requisites: | User account exists.
Step | Step Description | Expected Result
1 | Open Login Page | Login Page is displayed
2 | Enter valid email | Entered
3 | Enter incorrect password | Entered
4 | Click “Login” | Error message “Invalid email or password” appears
TC-CL-003
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page.
Description: | Verify login is blocked when email is not valid.
Pre-requisites: | None.
Step | Step Description | Expected Result
1 | Open Login Page | Page is displayed
2 | Enter email without “@” | Validation error appears
3 | Try clicking “Login” | Login does not proceed
TC-CL-004
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page.
Description: | Verify error when password field is empty.
Pre-requisites: | None.
Step | Step Description | Expected Result
1 | Open Login Page | Displayed
2 | Enter valid email | Accepted
3 | Leave password empty | —
4 | Click “Login” | Error: “Password required”
TC-CL-005
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify system trims whitespace in the email field.
Pre-requisites: | User account with confirmed email exists.
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter email with leading/trailing spaces (“ user@mail.com ”) | Email field accepts input
3 | Enter valid password | Password accepted
4 | Click “Login” | Whitespaces trimmed; user successfully logs in
TC-CL-006
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify that email is treated case-insensitively.
Pre-requisites: | User exists with lowercase email stored.
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter email in uppercase (USER@MAIL.COM) | Email accepted
3 | Enter valid password | Password accepted
4 | Click “Login” | User logs in successfully
TC-CL-007
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify that the system handles extremely long email input.
Pre-requisites: | None.
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter email longer than 256 chars | Validation error OR field prevents further input
3 | Enter valid password | Login does not proceed
TC-CL-008
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify UI behavior after several failed login attempts.
Pre-requisites: | User exists.
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter valid email + invalid password | Error message
3 | Repeat step 2 five times | Error repeats
4 | Try to login again | Message: “Too many attempts. Try again later.”
TC-CL-009
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify that password characters are masked.
Pre-requisites: | None
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter password | Password characters are masked with •••
TC-CL-010
Date | 2025-11-20
Tester | Vladimir
Project | Calmplete App
Module | Login Page
Description: | Verify that login can be submitted by pressing Enter key.
Pre-requisites: | User exists.
Step | Step Description | Expected Result
1 | Open Calmplete Login Page | Login Page is displayed
2 | Enter valid email | Accepted
3 | Enter valid password | Accepted
4 | Press Enter | User logs in successfully